## Sheet1
Basin Monitoring Task Force - Surface Water Monitoring Items Schedule
Calendar Year: | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029
Quarter: | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Procurement |  | QAPP & monitoring
QAPP Preparation
Initial Set up of WQ Monitoring Program (New Sites)
Performing of New Monitoring |  |  |  |  | New monitoring takes place once a quarter each year | [23 empty] | And beyond
Preparation of Annual Report | [28 empty] | And beyond
Comments/Finalization of Annual Report*
Basin Plan Amendment Update
Special Study Procurement
Special Study Implementation |  |  |  |  | Year 1 - development |  |  |  | Year 2 - monitoring, data collection |  |  |  | Year 3 - monitoring, data collection |  |  |  | Year 4 - analysis, documentation
WLAM Procurement
WLAM Update | [28 empty] | And beyond
*Annual Report due August 1 to Regional Board
Note on A6: Ian Achimore: No real deadline for QAPP in BP amendment order.
Note on A7: Ian Achimore: Two new sites, one historically done by OCWD. o one quarter for initial set up. Set up also includes figuring out the delivery logistics to nearby labs and their costs.
Note on A11: Ian Achimore: Will include language on new surface water monitoring process.
Note on A13: Ian Achimore: Figuring out surface water and groundwater interactions in reach 3 and reach 4